## TIckets
Requirements Traceability Matrix
Summary |  |  |  |  | Date update: Jan. 14, 2021
To Do | 0 | Minor | 74
In Progress | 7 | Major | 9
Done | 83 | Critical | 7
Remarks
ID | Defect | Severity | Status | Comment
Access Management |  |  |  |  | Dev Remarks January 4, 2020
MCB-001 | Access management - no success message. | Minor | Done | validated Jan. 2 release
MCB-002 | No mandatory change password and security question | Major | Done | validated Jan. 2 release
MCB-003 | Change password - confirm password field does not accept value. | Major | Done | validated Jan. 2 release
MCB-004 | Mandatory change password and sec question - display upon reseting password | Minor | Done | Acceptable for security purpose
MCB-005 | Admin LTE still accessible from MCB logo | Minor | Done | validated Jan. 5 release
MCB-006 | Set initial capital is accessible from dashboard | Major | Done | validated Jan. 5 release
MCB-007 | Inconsistent access for dashboard module | Critical | Done | Borrower management CRUD not accessible Validated Jan. 13 | borrower management is visible when employee mng is checked plus borrower mng is not visible when checked
MCB-008 | Report module is not accessible for user with grant access on reports | Critical | Done | validated Jan. 2 release
MCB-009 | Inconsistent access to report module | Critical | Done | validated Jan. 2 release
MCB-010 | Access Management - borrower view only not working | Critical | Done | validated Jan. 5 release
| Access Management - upon adding employee borrower appear also | Minor | Done | Validated Jan. 13
| Access Management - upon adding view borrower only edit also available | Minor | Done | Validated Jan. 13
| Access Management - total transaction is not visible upon giving access to user | Minor | Done | Removed Validated Jan. 13
Employee Management
MCB-011 | employee management - import employee - not dispalying added record | Major | Done | need verification with correct excel file
MCB-012 | My profile - employee notif - incorrect column name | Minor | Done | validated Jan. 2 release
MCB-013 | My Profile - Contact Details - incorrect start ID (start with ID-002) | Minor | Done | validated Jan. 5 release Based on overall refernce number of all employees. | Incremental yung ID, if back to 0, mag duduplicate na sila
MCB-014 | My Profile - Email Details - incorrect start ID (start with ID-002) | Minor | Done | validated Jan. 5 release Based on overall refernce number of all employees. | Incremental yung ID, if back to 0, mag duduplicate na sila
MCB-015 | My Profile - Address Details - incorrect start ID (start with ID-002) | Minor | Done | validated Jan. 5 release Based on overall refernce number of all employees. | Incremental yung ID, if back to 0, mag duduplicate na sila
MCB-016 | My Profile - Address Details - incorrect address label. Provice/City ¦ Municipality | Minor | Done | validated Jan. 5 release
MCB-017 | My Profile - Address Details - incorrect ID logged on audit logs | Minor | Done | Validated Jan. 11 Primary button causes inaccurate ID# | What do you mean?
MCB-018 | My Profile - Address Details - missing reactivate button | Minor | Done | Validated Jan. 11 | Deferred
MCB-019 | My Profile - Identification Details - missing reactivate button | Minor | In Progress | Validated Jan. 11 status not changing | Deferred
MCB-020 | Users Access Management - main category is not active upon saving | Minor | Done | Only selected to select all sub category, upon saving checkbox of main category will be unchecked. | What do you mean?
MCB-021 | Employee with Active status can't login | Critical | Done | Set default status to Active insteadt of regular Validated Jan. 11
| Employee under the manager only appears on the list of employees (for clarification) | Minor | Done | Validated Jan. 11
| Address tab - inoccrect audut logs upon reactivation | Minor | Done | Validated Jan. 13
| Edit profile - manager is not visible | Minor | In Progress | transferred manager not visible on dropdown
Borrower Management
MCB-022 | Borrower Management - Provicial address not working | Major | Done | validated Jan. 5 release
MCB-023 | Incorrect status color Active=Green | Minor | Done | validated Jan. 5 release | Saan ito?
MCB-024 | Must contain other filter options | Minor | Done | For improvement purpose | Like?
MCB-025 | Personal Reference cannot deactivate | Minor | Done | validated Jan. 5 release
MCB-026 | co-maker cannot deactivate | Minor | Done | Validated Jan. 11 | If reference number is used in an application, cannot deactivate. User must first deactivate record in application
MCB-027 | View spouse - remove submit button | Minor | Done | validated Jan. 5 release
MCB-028 | Spouse information - deactivate error message. | Minor | Done | validated Jan. 5 release
MCB-029 | Employment information ID - inocrrect start with 0002 | Minor | Done | validated Jan. 5 release Based on overall refernce number of all employees. | Incremental yung ID, if back to 0, mag duduplicate na sila
MCB-030 | Borrower Address Information - incorrect label - Provice/Municipality | Minor | Done | Validated Jan. 11 | What do you mean?
MCB-031 | Address Information - incorrect ID | Minor | Done | validated Jan. 5 release Based on overall refernce number of all employees. | What do you mean?
MCB-032 | Address Information - cannot deactivate | Minor | Done | validated Jan. 5 release | What do you mean?
MCB-033 | Email Information - incorrect audit logs ID upon adding new email | Minor | Done | validated Jan. 11 release | Incremental yung ID, if back to 0, mag duduplicate na sila
| List of borrower - Added by column - NA mark dispalyed | Minor | Done | for reference purpose validated Jan. 11
| Viewing of borrowers - depends on branches | Minor | Done | validated Jan. 11 release | All records must be visible for everyone
| Borrower picture via webcam - corrupted | Minor | Done | validated Jan. 11 release Flexi browser Recommended Chrome
| Upon changing profile picture - system show user has no access | Minor | Done | validated Jan. 11 release Flexi browser Recommended Chrome
Loan Management
MCB-034 | Loan Application report - incorrect business logo | Minor | Done | validated Jan. 5 release
MCB-035 | Audit logs for new loan application - not recorded | Minor | Done | recorded on history logs
MCB-036 | loan application - 2nd action column - not applicable | Minor | Done | validated Jan. 5 release | What do you mean?
MCB-037 | Restructure terms for repayment -incorrect | Minor | Done | validated Jan. 5 release Shows the amount of payment | What do you mean?
MCB-038 | Repayment Cycle - no history logs | Minor | Done | validated Jan. 5 release | What do you mean? May record naman sa history logs
MCB-039 | Purpose - no history logs | Minor | Done | validated Jan. 5 release | What do you mean? May record naman sa history logs
MCB-040 | Repayment Cycle - with error message if try to deactivate | Minor | Done | Cannot be deactivate if currently using
MCB-041 | Loan Status - no available actions | Minor | Done | Only newly added status is for editing. System generated status are not to be edited | Only newly added status is for editing. System generated status are not to be edited
| Additional Charges - upon editing the value some value are missing | Major | Done | Validated Jan. 11 | Upon renewal, Additional charges percentages becomes flate rate
| Loan Application - History logs tab -removed action column | Minor | Done | Validated Jan. 11
| Restructure payment is not recorded on payment | Minor | Done | Payment through collections by Others. Validated Jan. 11
| No deactivate button for collateral | Minor | Done | Validated Jan. 13 No deactivate button but with status record
| Requirements - requirementws type field does not have value | Minor | Done | Validated Jan. 13
| Monthly Obligation - change status to active instead of regular | Minor | In Progress | plain color instead of green
| Co-maker - incorrect value for full name column | Minor | Done | Validated Jan. 13
| Co-maker - education tab incorrect fileds upon adding record | Minor | Done | Validated Jan. 13
| Removed default value on DB for Myrna comment Ref No. COM-000019 | Minor | In Progress | Status color
| Loan renewal - loan release date - invalid date | Major | Done | Validated Jan. 13
| Loan renewal - requirements section - php error | Critical | Done | Validated Jan. 13
| Loan approval - incorrect arrangement of approver | Minor | Done | Validated Jan. 13
| Loan Approval - name of imported borrower is not visible | Minor | In Progress
| View loan - branch is missing on data table | Minor | In Progress
Collection Management
MCB-042 | Collection Management - not working properly | Critical | Done | Validated
MCB-043 | Collection management - Filter - incorrect result | Minor | Done | Validated | What's the prob?
Asset Management
MCB-044 | Categories - no history logs for new category | Minor | Done | Validated
MCB-045 | Assigned employee - not visible upon editing | Minor | Done | Validated
MCB-046 | Display assigned employee on data table | Minor | Done | Validated Jan. 13
| Asset Management - Filter not working | Minor | Done | Validated Jan. 13
Financial Management
MCB-047 | Type of deposit - error message upon editing | Minor | Done | Validated Jan. 13
MCB-048 | Type of expense - error message upon editing | Minor | Done | Validated Jan. 13
MCB-049 | Add deposit - not working | Major | Done | Validated Jan. 13
System Setup
MCB-050 | History logs - Changed temporary password appear randomly upon opening logs. | Minor | Done | Validated Jan. 13
MCB-051 | Disbursnment - reactivate with error message | Minor | Done | Validated Jan. 13
MCB-052 | Disbursment - add new record - Database error | Minor | Done | Validated Jan. 13
MCB-053 | Initial Capital - created by - emp number id displayed | Minor | Done | Validated Jan. 13
MCB-054 | Initial Capital - remove set primary button | Minor | Done | Validated Jan. 13
MCB-055 | Mode of payment - reactivate button is missing | Minor | In Progress
MCB-056 | Mode of payment - canbnot be deactivated | Minor | Done | Validated Jan. 13
Reports
MCB-057 | Print history logs - not working | Minor | Done | Validated Jan. 13
MCB-058 | Income statement - incorrect browser name | Minor | Done | Validated Jan. 13
MCB-059 | History logs - remove remarks columns on generated PDF | Minor | Done | Validated Jan. 13 Remarks retain for reference
MCB-060 | Loan Collection - PHP error upon generating | Major | Done | Validated Jan. 13
MCB-061 | expenses - incorrect browser name | Minor | Done | Validated Jan. 13
MCB-062 | Demographics - no date dispalyed for age | Minor | Done | Validated Jan. 13
MCB-063 | Loan extended - primary is dispalying for loan type | Minor | Done | Validated Jan. 13
Dashboard
MCB-059 | Daily Distbursment - unauthrize access | Minor | Done | Validated Jan. 13
MCB-060 | Dashboard tile is missing | Minor | Done | Depends on zoom percentage Validated
Asset Management - assets assigned to the loggedi n employee are visible

## Steps to replicate
Ticket ID | Defect | Steps | Comment
MCB-006 | Set initial capital is accessible from dashboard | 1. Add new user.
2. Go to Access Management of creted user
3. Add dashbaord module
4. Login using created user
5. on Dashboard, click more info link on Daily Disbursment
MCB-007 | Inconsistent access for dashboard module | 1. Add new user.
2. Go to Access Management of creted user
3. Under loan mangement category, select only view loans.
MCB-010 | Access Management - borrower view only not working | 1. Add new user.
2. Go to Access Management of creted user
3. Under borrower module, select only view borrower
MCB-013 | My Profile - Contact Details - incorrect start ID (start with ID-002) | 1. Create employee | applicable to all related defects
2. Go to employee profile
3. Add contact details
4. Reference number start with 0002 insteqad of 0001
MCB-017 | My Profile - Address Details - incorrect ID logged on audit logs | 1. Create employee
2. Go to employee profile
3. Add address details
4. Reference number start on audot logs is different on address tab
MCB-021 | Employee with Active status can't login | 1. Create employee
2. Create user account
3. Go to employee management
4. Edit profile, change status from regular to active
MCB-045 | Assigned employee - not visible upon editing | 1. Add asset
2. Upon adding assign emploiyee
3. Click edit button
4. Check assgiened employee dropdown, no value