## Business Requirements
M.C. BILIBER e-Lending Tool Business Requirments
# | BUSINESS REQUIREMENTS
Access Management
1 | Employee must able to access the system using given credentials.
2 | The following will be the credentials of the employees in order to access the system
2.1 | User ID: Employee Number
2.2 | Password: Employee Number (Default)
3 | Employees must be redirected to corresponding user interface based on assigned roles on the users management setup.
4 | The following are the roles exist on the system:
4.1 | system administrator
4.2 | collector
4.3 | top management
4.4 | employee/loan officer
5 | The employess must able to return to login page upon clicking the logout button.
6 | Employee must able to select 3 security question from the available list
7 | Employees must able to fillup security questions on the 1st instance of login.
8 | The following are the security questions available:
8.1 | What is the name of your favorite pet?
8.2 | What is the name of your childhood friend?
8.3 | What is your favorite color?
8.4 | Who is your favorite writer?
8.5 | What is the first model of your car?
8.6 | How long is your first relationship?
8.7 | What is your favorite place?
8.8 | How much is your first salary?
8.9 | What is you mother maiden name?
8.1 | What is the name of your youngest sibling?
9 | Employee must change default password on first login instance only.
10 | Employee must be able to request for a reset password.
11 | Employee must able to provide employee number and answer 3 security question correctly in order to proceed the request.
12 | Assigned manager of the employee must be notify on the request.
13 | Employee must able to change the password anytime by providing the folloiwing:
13.1 | Current password
13.2 | New password
13.3 | Confirm New Password (retype new password)
14 | Password format must comply on the following:
14.1 | Composed of more that 15 characters;
14.2 | Must have 1 uppercase letter;
14.3 | Must have 1 special character;
15 | Employee must see a text regarding composition of password.
16 | Assigned manager must be notified for the credentials of newly hired employee such us:
16.1 | Employee Profile
16.2 | Employee ID
16.3 | Default Password
Users Management
17 | Assigned employee will be known as system admistrator and must be able to add employee records using the system
18 | The following categories must be included in adding new record:
18.1 | Personal Inforamtion
18.2 | Contact Information
18.3 | Business Inforamtion
18.4 | Access Inforamtion
19 | The following details must be included under Personal Information category
19.1 | First Name*
19.2 | Last Name*
19.3 | Middle Name
19.4 | Extension Name
19.5 | Birth Date*
19.6 | Gender
20 | The following details must be included under Contact Information category
20.1 | Contact Number*
20.2 | Personal Email*
21 | The following details must be included under Business Information category
21.1 | Business Email
21.2 | Employee Number*
21.3 | Position
21.4 | Assigned Manager
21.5 | Branch
22 | The following details must be included under Access Information category
22.1 | Role*
23 | Assigned manager must be notified once new employee is added.
24 | Notification must contain the employees name and employee number as well as the default password given.
25 | System Adminsitrator must able to do the following:
25.1 | To update employees' information
25.2 | Employee must be notified for any changes on respective information.
25.3 | To deactivete employees' account.
25.4 | To activate employee's account
25.5 | Assigned manager must be notified upon activation or deactivation of employee.
25.6 | To import excel file contains employee details
25.7 | To view the list of active and inactive employees.
25.8 | To filter the list of employees using the following parameters:
25.9 | Branch
25.1 | Status
25.11 | Position
25.12 | Roles
25.13 | Manager
25.14 | To search employees based on their first name, last name ,or employee number.
25.15 | To view the count of employees based on the following:
25.16 | Status
25.17 | Branch
25.18 | Position
Dashboard
26 | Dashbaord must be able no all users of the system such as system adminsitrator, employee, collector, and top management.
26.1 | Top management dashboard must contains the following:
26.2 | Current fund of the business;
26.3 | Total expenses of the business per day;
26.4 | Total income of the business per day;
26.5 | Number of transctions per day;
26.6 | Number of approved loans per day;
26.7 | Population of clients based on location;
26.8 | Expenses of the business per category of assests;
26.9 | Population of clients based on Demographic profile such as: (arrangd per year)
26.1 | A. Age
26.11 | 18-24 years old
26.12 | 25-31 years old
26.13 | 32-39 years old
26.14 | 40-47 years old
26.15 | 48-55 years old
26.16 | 56-65 years old
26.17 | Above 65 years old
26.18 | Education
26.19 | No grade completed
26.2 | Pre-school
26.21 | Some Elementary
26.22 | Elementary Graduate
26.23 | Some High School
26.24 | High School Graduate
26.25 | Post-Secondary
26.26 | College Undergradute
26.27 | College Graduate
26.28 | Post-Baccalaureate
26.29 | Gender/Sex
26.3 | Male
26.31 | Female
26.32 | Occupation
26.33 | Technicians and associate professinoals
26.34 | Professional
26.35 | Clerical and Support Worker
26.36 | Pland and Machine Operator and Assembler
26.37 | Craft and Related Trade Worker
26.38 | Skilled Agricultural, Forestry, and Fishery Worker
26.39 | Service and Sales Worker
26.4 | Manager
26.41 | Others *Please specify*
26.42 | Income Level
26.43 | Less than PHP 9,250.00
26.44 | PHP 9,250.00 - PHP 19,040.00
26.45 | PHP 19,041.00 - PHP 38,080.00
26.46 | PHP 38,081.00 - PHP 66,640.00
26.47 | PHP 66,641.00 - PHP 114,240.00
26.48 | PHP 114,241.00 - PHP 190,400.00
26.49 | More than PHP 190,400.00
26.5 | Marital Status
26.51 | Single
26.52 | Married
26.53 | Widowed
26.54 | Separated
26.55 | Others *Please specify*
26.56 | B. Risk Borrower Profile
26.57 | Low Risk
26.58 | Medium Risk
26.59 | High Risk
26.6 | C. Number of rollovers/refinance borrowers/ and one time borrowers
26.61 | Numbers based on Historical Data on Loans extended by the company such as: (arrangd per year)
26.62 | A. Total Number of borrowers
26.63 | B. Total Number of Loans
26.64 | C. Geographical concentration
26.65 | National Capital Region;
26.66 | Luzon;
26.67 | Visayas;
26.68 | Mindanao
26.69 | D. Types of Loan
26.7 | E. Total loan amount
26.71 | F. Tenors
26.72 | G. Interest Rates
26.73 | H. Fees and other charges please specify
26.2 | Collector dashboard must contains the following:
26.75 | Daily transaction
26.76 | Number of transaction per day
26.77 | Total Collection
26.78 | List of active loans
26.3 | Employee dashbaord must contains the following:
26.8 | List of clients
26.81 | Laons approval - for selected employees only
26.82 | Number of transactions
26.83 | Latest transactions
26.4 | System Admnistrator dashboard contains the following:
26.85 | List of active and inactive employees.
26.86 | Number of system users/employees
26.87 | Audit Trails
Setup and Configuration
27 | Admin or employee should be able to add loan details to be used in the loan application
28 | Employee or admin should be able to add loan details such as:
28.1 | Name
28.2 | Description
29 | Admin or employee should be able to add loan undertaking for the system to use
30 | Admin or employee should be able to add conditional charges to be charged in a loan application such as:
30.1 | Type of charge (Percent or fixed amount)
30.2 | Name
30.3 | Description
30.4 | Frequency
31 | Admin or employee should be able to add a requirement checklist for an application loan
32 | Admin or employee should be able to add interests for an application loan
33 | Admin or employee should be able to add bank details for the system to use such as their:
33.1 | Name
33.2 | Description
33.3 | Account Number (optional)
34 | Admin should be able to add branch details such as:
34.1 | Name
34.2 | Description
34.3 | Date of lease
34.4 | Monthly lease
35 | Admin should be able to change the details of a branch
36 | Admin should be able to change the logo of the system
37 | Admin or employee should be able to setup the type of charges to be used in the system
38 | Admin or employee should be able to add payment cycle to be used in loan application
39 | Admin should be able to add or edit loan status to be used in the system
40 | Admin should be able to set initial capital to be used throughout the system by the collector or assigned employee
41 | Admin should be able to add/edit or remove an asset category for the system to use in supply management
42 | Admin should be able to add/edit or remove a purpose to the system for the loan application to use
43 | Admin should be able to add/edit or remove optional charges to the system for the loan application to use
44 | Admin should be able to add/edit or remove employee position to be used in adding employees
Supply Management
45 | Admin should be able to add asset types such as its:
45.1 | Name
45.2 | Category
46 | Admin or assigned employee should be able to add assets to the system and their details such as:
46.1 | Type
46.2 | Date of valuation
46.3 | Value
46.4 | Purchase date
46.5 | Purchase price
46.6 | Replacement value
46.7 | Serial Number (if any)
46.8 | Bought from (if applicable)
46.9 | Description
46.10 | Supporting files
Borrower Management
47 | The following categories must be included in adding new of customer record:
47.1 | Personal Information
47.2 | Contact Information
47.3 | Employment Information
47.4 | Personal References
47.5 | Co-Maker Information
47.6 | Spouse Information
47.7 | Address Information
47.8 | Customer Identification Information
48 | The following details must be included under Personal Information category
48.1 | First Name*
48.2 | Last Name*
48.3 | Middle Name
48.4 | Extension Name
48.5 | Birth Date*
48.6 | Gender
48.7 | Civil Status
48.8 | No of Dependents
48.9 | Birthplace
49 | The following details must be included under Contact Information category
49.1 | Contact Number*
49.2 | Email*
50 | The following details must be included under Employment Information category
50.1 | Present employer/business
50.2 | Position title
50.3 | Date hired
50.4 | Telephone no
50.5 | Employment tenure
50.6 | Business address
50.7 | Previous employer/business
50.8 | Previous employer position title
50.9 | Previous employer telephone no
50.10 | Previous employer employment tenure
50.11 | Previous employer address
51 | The following details must be included under Personal References category
51.1 | Name
52.2 | Address
52.3 | Telephone no.
52 | The following details must be included under Spouse Information category
49.1 | First Name*
49.2 | Last Name*
49.3 | Middle Name
49.4 | Extension Name
49.5 | Birth Date*
49.6 | Gender
49.7 | Civil Status
49.8 | No of Dependents
49.9 | Birthplace
53 | The following details must be included under Co-Maker Information category
53 | First Name*
53 | Last Name*
53 | Middle Name
53 | Extension Name
53 | Present employer/business
53 | Position title
53 | Date hired
53 | Telephone no
53 | Employment tenure
53 | Business address
54 | The following details must be included under Address Information category | Add collection
53 | City Address
53 | Provincial Address
53 | Length of stay at city address
53 | Telephone at city address
53 | Resident type
55 | The following details must be included under Customer Identification Information category | Add Reports
52.1 | ID Name
52.2 | ID Number
Uploading of supporting documents
Loan Application
Upon adding the borrowers information successfully, the applicant can proceed to the Loan Application form
If a borrower does not exist in the system, the applicant must fill up the necessary details at the Borrower Management Module
If a borrower does exist in the system, the applicant must fill up the necessary details such as:
Source:
Walk-in
Through Agent
Agent's Name
Term:
3 months
6 months
12 months
Purpose:
Appliance
Education
Personal Use
Hospitalization
Amount Applied for:
The following details must be included under the Applicant's Household Monthly Net Income:
Sources of other income
Details
Amount
Monthly Expenses
Own Monthly Salary
Spouse's Monthly Salary
Other Expenses
The system can display the risk assessment of an applicant based on their birthdate, monthly expenses, salary and monthly obligations
The applicant must also submit the following requirements for the application:
For Employed:
Completely filled out application form
Photocoty of valid IDs
Photocopy of latest Utility Bill
Photocopy of ID issued by the employer with photo and signature
ATM Payroll card statement (3 months)
Latest Pay Slip
ATM Payroll
For Self Employed:
Completely filled out application form
Photocopy of valid IDs
Photocopy of latest Utility Bill
Photocopy of latest ITR
Credit Card billing statement (3 months)
Business Papers (DTI registration/Business Permit/SEC)
Audited Financial Statements for the last 2 years
Trade References
Other Documents
After submitting the necessary requirements for the loan application, the employee can now set the approval workflow.
Upon the approval of the Loan Application, the following must be included for the disclosure statement on loan/credit transactions
Additional Charges:
Interest Rate
Add-On Interest Rate
Payment Schedule:
Amount Payable with each installment
No. of Installments
Conditional Charges:
Collection Management
The user must be able to add a collection record in the collection management module with the following details:
Loan Name
Amount of the Collection
Method of Payment
Change
Collection Date
The user can add/edit or remove a collector per Loan

## Task
MCB e-Lending Task List
Summary
To Do | 118
In Progress | 12
Done | 27
Total: | 157
% | 17.2%
Sprint | Task | Assigend | Status | Date Started | Date Finished | % | Note
0 | Requierments Gathering Access Management | Ian/Amity | In Progress | 07/27/2020 |  | 71.42%
0.1 | Requirements Gathering | Ian/Amity | In Progress | 07/28/2020 | 2020-06-08 | 55.33%
0.1.1 | Business Requirement | Ian | In Progress | 07/28/2020 |  | 99% | for consolidation
0.1.1.1 | Access Management | Ian | Done | 07/28/2020 | 07/28/2020 | 100%
0.1.1.2 | Users Management | Ian | Done | 07/29/2020 | 07/29/2020 | 100%
0.1.1.3 | Setup Configuration | Amity | Done | 07/28/2020 | 07/28/2020 | 100%
0.1.1.4 | Dashbaord | Ian | Done | 07/29/2020 | 2020-01-08 | 100%
0.1.1.5 | Customer profiling | Amity | Done | 07/29/2020 | 07/29/2020 | 100%
0.1.1.6 | Loan Application and Monitoring | Ian and Amity | Done | 2020-01-08 | 2020-01-08 | 100%
0.1.1.7 | Collection Monitoring | Ian and Amity | Done | 2020-01-08 | 2020-01-08 | 100%
0.1.1.8 | Supply Management | Amity | Done | 2020-01-08 | 2020-01-08 | 100%
0.1.1.9 | Reports | Ian | Done | 2020-01-08 | 2020-01-08 | 100%
0.1.2 | Business Requirement Review | Ian/Amity | Done | 2020-06-08 | 2020-06-08 | 100%
0.1.3 | Business Requirement Consolidation | Ian | In Progress | 2020-06-08 |  | 99% | with review points
0.1.4 | Functional Requirements | John/Amity | To Do |  |  | 0%
0.1.5 | Functional Requirements Review | Ian/Amity | To Do |  |  | 0%
0.1.6 | Database Standards | Ian | Done | 2020-05-08 | 2020-05-08 | 100%
0.1.7 | Database Standards Review | Amity | Done | 2020-06-08 | 2020-06-08 | 100%
0.1.8 | Requierments Discussion | MCB | To Do |  |  | 0%
0.1.9 | Signing Off | MCB | To Do |  |  | 0%
0.2 | Access Management | John | Done | 07/27/2020 | 8/42020 | 87.5%
0.2.1 | Login | John | Done | 07/28/2020 | 07/28/2020 | 100%
0.2.2 | Mandatory change password | John | Done | 07/28/2020 | 07/28/2020 | 100%
0.2.3 | Reset Password | John | Done | 07/29/2020 | 07/29/2020 | 100%
0.2.4 | Change Password | John | Done | 07/29/2020 | 07/29/2020 | 100%
0.2.5 | Security Question | John | Done | 07/30/2020 | 07/30/2020 | 100%
0.2.6 | Reset Password Notification - manager | John | Done | 07/30/2020 | 2020-04-08 | 100%
0.2.7 | New Created Account Notification - manager | John | Done | 07/30/2020 | 2020-04-08 | 100%
0.2.8 | QA Testing | Ian | To Do |  |  | 0%
1 | Database Users Management Customer Profiling | Ian/Amity | In Progress |  |  | 51.43%
1.1 | Database | Ian/Amity | In Progress | 2020-06-08 |  | 90%
1.1.1 | ERD | Amity | In Progress | 2020-06-08 |  | 90%
1.1.2 | Database Script | Amity | In Progress | 2020-06-08 |  | 90%
1.1.3 | Database Diagram | Amity | In Progress | 2020-06-08 |  | 90%
1.1.4 | Requirements Mapping | Ian | In Progress | 2020-06-08 |  | 90%
1.2 | Users Management | John | In Progress | 2020-04-08 |  | 50%
1.2.1 | Add user/employee | John | Done | 2020-04-08 | 2020-04-08 | 100% | for adjustment
1.2.2 | Newly Hired employee notification - manager | John | Done | 2020-04-08 | 2020-04-08 | 100%
1.2.3 | Update User | John | Done | 2020-04-08 | 2020-04-08 | 100% | for adjustment
1.2.4 | Employee update notification - employees | John | To Do |  |  | 0%
1.2.5 | Deactivate User | John | Done | 2020-04-08 | 2020-04-08 | 100% | for adjustment
1.2.6 | Activate User | John | Done | 2020-04-08 | 2020-04-08 | 100% | for adjustment
1.2.7 | Activate and Deactivate Notification - manager | John | To Do |  |  | 0%
1.2.8 | Import Users | John | To Do |  |  | 0%
1.2.9 | List of users view | John | Done | 2020-04-08 | 2020-04-08 | 100% | for adjustment
1.2.10 | List of Users Filter | John | To Do |  |  | 0%
1.2.11 | Search / Search Filter | John | To Do |  |  | 0%
1.2.12 | QA Testing | Ian | To Do |  |  | 0%
1.3 | Customer profiling | John | In Progress | 2020-04-08 |  | 14.29%
1.3.1 | Add customer | John | Done | 2020-04-08 | 2020-04-08 | 100%
1.3.2 | Archiving | John | To Do |  |  | 0%
1.3.3 | Update customer | John | To Do |  |  | 0%
1.3.4 | Delinquent Tagging | John | To Do |  |  | 0%
1.3.5 | Viewing of loan history | John | To Do |  |  | 0%
1.3.6 | Viewing of payments | John | To Do |  |  | 0%
1.3.7 | QA Testing | John | To Do |  |  | 0%
2 | Loan Application and Monitoring | Ian/Amity | To Do |  |  | 0%
2.1 | Loan Application and Monitoring | John | To Do |  |  | 0%
2.1.1 | Loan Application - ustomer cashflow | John | To Do |  |  | 0%
2.1.2 | Risk Assessment | John | To Do |  |  | 0%
2.1.3 | Loan Calculator | John | To Do |  |  | 0%
2.1.4 | Approval | John | To Do |  |  | 0%
2.1.5 | Viewing of loans (by category) | John | To Do |  |  | 0%
2.1.6 | Search | John | To Do |  |  | 0%
2.1.7 | QA Testing | Ian | To Do |  |  | 0%
3 | Collection Monitoring Supply Management | Ian/Amity | To Do |  |  | 0%
3.1 | Collection Monitoring | John | To Do |  |  | 0%
3.1.1 | Payment Collection | John | To Do |  |  | 0%
3.1.2 | Viewing of collection | John | To Do |  |  | 0%
3.1.3 | Search / Search Filter | John | To Do |  |  | 0%
3.1.4 | QA Testing | Ian | To Do |  |  | 0%
3.2 | Supply Management | John | To Do |  |  | 0%
3.2.1 | Adding assets | John | To Do |  |  | 0%
3.2.2 | Viewing of assets amount per item | John | To Do |  |  | 0%
3.2.3 | Viewing of assets amount per category | John | To Do |  |  | 0%
3.2.4 | Search / Search Filter | John | To Do |  |  | 0%
3.2.5 | QA Testing | Ian | To Do |  |  | 0%
4 | Setup Configuration Dashboard Report | Ian/Amity | To Do |  |  | 0%
4.1 | Setup Configuration | John | To Do |  |  | 0%
4.1.1 | Employee Position | John | To Do |  |  | 0%
4.1.2 | Branch | John | To Do |  |  | 0%
4.1.3 | Logo | John | To Do |  |  | 0%
4.1.4 | Requirements | John | To Do |  |  | 0%
4.1.5 | Loan Details | John | To Do |  |  | 0%
4.1.6 | Loan undertaking | John | To Do |  |  | 0%
4.1.7 | Assest category | John | To Do |  |  | 0%
4.1.8 | Initial capital | John | To Do |  |  | 0%
4.1.9 | Interest Rate | John | To Do |  |  | 0%
4.1.10 | Purpose | John | To Do |  |  | 0%
4.1.11 | Conditional charges | John | To Do |  |  | 0%
4.1.12 | Optional charges | John | To Do |  |  | 0%
4.1.13 | Payment Cycle | John | To Do |  |  | 0%
4.1.14 | Loan Status | John | To Do |  |  | 0%
4.2 | Dashboard | John | To Do |  |  | 0%
4.2.1 | Top Management | John | To Do |  |  | 0%
4.2.1.1 | Current Fund | John | To Do |  |  | 0%
4.2.1.2 | Total expense per day | John | To Do |  |  | 0%
4.2.1.3 | Total Income per day | John | To Do |  |  | 0%
4.2.1.4 | Number of transction | John | To Do |  |  | 0%
4.2.1.5 | Number of approved loans per day | John | To Do |  |  | 0%
4.2.1.6 | Population of client based on location | John | To Do |  |  | 0%
4.2.1.7 | Expesnes of business for assets per category | John | To Do |  |  | 0%
4.2.1.8 | Population -age | John | To Do |  |  | 0%
4.2.1.9 | Population - education | John | To Do |  |  | 0%
4.2.1.10 | Population - gender | John | To Do |  |  | 0%
4.2.1.11 | Population - occupation | John | To Do |  |  | 0%
4.2.1.12 | Population - income level | John | To Do |  |  | 0%
4.2.1.13 | Population - marital status | John | To Do |  |  | 0%
4.2.1.14 | Population - risk barrower profile | John | To Do |  |  | 0%
4.2.1.15 | Population - rollovers/refinance borrowers/ and one time borrowers | John | To Do |  |  | 0%
4.2.1.16 | Population - number of borrowers | John | To Do |  |  | 0%
4.2.1.17 | Population - number of loans | John | To Do |  |  | 0%
4.2.1.18 | Population - geographical concentration | John | To Do |  |  | 0%
4.2.1.19 | Population - types of loans | John | To Do |  |  | 0%
4.2.1.20 | Total loan amount per year | John | To Do |  |  | 0%
4.2.1.21 | Tenors | John | To Do |  |  | 0%
4.2.1.22 | Total Interest rates | John | To Do |  |  | 0%
4.2.1.23 | Total Fees and other charges please specify | John | To Do |  |  | 0%
4.2.2 | Collector | John | To Do |  |  | 0%
4.2.2.1 | Daily Transaction | John | To Do |  |  | 0%
4.2.2.2 | Number of transction per day | John | To Do |  |  | 0%
4.2.2.3 | Total collection per day | John | To Do |  |  | 0%
4.2.2.4 | List of active loans | John | To Do |  |  | 0%
4.2.3 | Employee | John | To Do |  |  | 0%
4.2.3.1 | List of clients | John | To Do |  |  | 0%
4.2.3.2 | Loans approval | John | To Do |  |  | 0%
4.2.3.3 | number of transactions | John | To Do |  |  | 0%
4.2.3.4 | Latest of transactions | John | To Do |  |  | 0%
4.2.4 | System Administrator | John | To Do |  |  | 0%
4.2.4.1 | List of employees | John | To Do |  |  | 0%
4.2.4.2 | number of users | John | To Do |  |  | 0%
4.2.4.3 | Audit trails | John | To Do |  |  | 0%
4.3 | Reports | John | To Do |  |  | 0%
4.3.1 | Collection Report | John | To Do |  |  | 0%
4.3.2 | Income Statement | John | To Do |  |  | 0%
4.3.3 | Expense Report | John | To Do |  |  | 0%
4.3.4 | List of Loans | John | To Do |  |  | 0%
4.3.5 | Transaction List | John | To Do |  |  | 0%
5 | RTM Regression Documentation | Ian/Amity | To Do |  |  | 0
5.1 | RTM | Amity | To Do |  |  | 0%
5.2 | Regression Testing | Ian | To Do |  |  | 0%
5.2.1 | Access Management | Ian | To Do |  |  | 0%
5.2.2 | Users Management | Ian | To Do |  |  | 0%
5.2.3 | Customer profiling | Ian | To Do |  |  | 0%
5.2.4 | Loan Application and Monitoring | Ian | To Do |  |  | 0%
5.2.5 | Collection Monitoring | Ian | To Do |  |  | 0%
5.2.6 | Supply Management | Ian | To Do |  |  | 0%
5.2.7 | Setup and Configuration | Ian | To Do |  |  | 0%
5.2.8 | Dashboard | Ian | To Do |  |  | 0%
5.2.9 | Reports | Ian | To Do |  |  | 0%
5.3 | Documentation | Ian | To Do |  |  | 0
5.3.1 | SRS | Ian | To Do |  |  | 0%
5.3.2 | SS | Ian | To Do |  |  | 0%
5.3.3 | SDS | Ian | To Do |  |  | 0%
5.3.4 | User's Manual | Amity | To Do |  |  | 0%
5.3.5 | Peer Review | Ian/Amity | To Do |  |  | 0%
5.3.6 | Training Manual | Ian/Amity | To Do |  |  | 0%

## Sprint Schedule
MCB e-Lending Master Schedule
Summary
Sprint Velocity: | 2 weeks sprint
Date Started: | July 27, 2020
Project Deadline: | January 20, 2021
Deployment Date: | October 24, 2020
To Do | 6
In Progress | 1
Done | 0
Total | 7
% | 0%
Sprint # | Start Date | End Date | Content | Status | %
0 | 07/27/2020 | 2020-07-08 | Requirements Gathering | In Progress | 80%
1 | 2020-10-08 | 08/21/2020 | Database Users Management Customer Profiling | To Do | 0%
2 | 08/24/2020 | 2020-04-09 | Loan Applciation and Monitoring | To Do | 0%
3 | 2020-07-09 | 2020-11-09 | Collaction Monitoring and Supply Management | To Do | 0%
4 | 09/14/2020 | 09/25/2020 | Setup and Configuration Dashboard Reports | To Do | 0%
5 | 09/28/2020 | 2020-09-10 | RTM Regression Testing Documentation | To Do | 0%
6 | 2020-12-10 | 10/23/2020 | Bug Fixing Deployment Training | To Do | 0%
TOTAL: |  |  |  |  | 11.43%

## Retorspective
MCB e-Lending Dev Team Rertrospective
Sprint: | 0
Period: | July 27, 2020 - Aug. 7, 2020
Velocity: | 2 Weeks
Includes: | Requirements Gathering
Access Management
Dev Team | What something good happened? | What I want to change? | What I learned?
Ian
Amity
John